## Team
ProductName
Release Version | v8.0
Planning Date: | 2017-01-16
Release Date: | 2017-05-03
Team
Name | Role | Location
TeamMember1 | Sr. Developer | Remote - HCL
TeamMember2 | Developer | Remote - HCL
TeamMember3 | QA | Remote - HCL
TeamMember4 | QA | Office - Wallingford
TeamMember5 | Documentation | Office - Birmingham/Remote
TeamMember6 | Scrum Master | Office - Birmingham
TeamMember7 | BA | Office - Birmingham
TeamMember8 | Sr. Dev Manager | Office - Birmingham
TeamMember9 | PM | Remote
TeamMember10 | PO | Office - Wallingford

## Team Velocity
*Please update items in RED
Team Members | Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6 |  |  | Sprint 7 |  |  | Srpint 8 (1 WK HIP) |  |  | Cumulative
| 2017-01-17 | - | 2017-01-30 | 2017-01-31 | - | 2017-02-13 | 2017-02-14 | - | 2017-02-27 | 2017-02-28 | - | 2017-03-13 | 2017-03-14 | - | 2017-03-27 | 2017-03-28 | - | 2017-04-10 | 2017-04-11 | - | 2017-04-24 | 2017-04-25 | - | 2017-05-01
| Load | PTO | Holiday | Load | PTO | Holiday | Load | PTO | Holiday | Load | PTO | Holiday | Load | PTO | Holiday | Load | PTO | Holiday | Load | PTO | Holiday | Load | PTO | Holiday | Load | PTO | Holiday
TeamMember1 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 4 | 0 | 0 | 60 | 0 | 0
TeamMember2 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 4 | 0 | 0 | 60 | 0 | 0
TeamMember3 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 5 | 0 | 0 | 75 | 0 | 0
TeamMember4 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | 5 | 0 | 0 | 75 | 0 | 0
Total | 36 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 36 | 0 | 0 | 18 | 0 | 0 | 270 | 0 | 0
PTO + Holiday | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
Unplanned (15% of Load) | 5.4 |  |  | 5.4 |  |  | 5.4 |  |  | 5.4 |  |  | 5.4 |  |  | 5.4 |  |  | 5.4 |  |  | 2.7 |  |  | 40.5
Bug Fixes (20% of Load) | 7.2 |  |  | 7.2 |  |  | 7.2 |  |  | 7.2 |  |  | 7.2 |  |  | 7.2 |  |  | 7.2 |  |  | 3.6 |  |  | 54
Enhancement \ Regulatory (65% of Load) | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 18 |  |  | 9 |  |  | 175.5
Team Capacity |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 36 |  |  | 18 |  |  | 270
144
180
Memorial Day | 0
216
252
270

## Objective
SIS Team Objective |  | Delivery | Business Value
1 | Item 1 | Prod v.Y | 10
2 | Item 2 | Prod v.Y | 10
3 | Item 3 | Prod v.Y | 10
4 | Item 4 | Prod v.Y | 9
5 | Item 5 | Prod v.Y | 9
6 | Item 6 | Prod v.Y | 8
7 | Item 7 | Prod v.Y | 7
8 | Item 8 | Prod v.Y | 7
9 | Item 9 | Prod v.Y | 3
10
11
12
13
14
Stretch Goals - [List out stretch goals]

## Release Board
| Sprint 1 |  |  | Sprint 2 |  |  | Sprint 3 |  |  | Sprint 4 |  |  | Sprint 5 |  |  | Sprint 6 |  |  | Sprint 7 |  |  | Srpint 8 (1 WK HIP)
| 2017-01-17 | - | 2017-01-30 | 2017-01-31 | - | 2017-02-13 | 2017-02-14 | - | 2017-02-27 | 2017-02-28 | - | 2017-03-13 | 2017-03-14 | - | 2017-03-27 | 2017-03-28 | - | 2017-04-10 | 2017-04-11 | - | 2017-04-24 | 2017-04-25 | - | 2017-05-01
Delivery |  |  |  | 2/13 - Prod vX |  |  | 2/27 - vY Interim Build for InterOp | [11 empty] | 4/24 - StRpt vX 4/17 - Prod vY Interim Build to InterOp (Windows 2016) |  |  | 5/3 - Prod vY
Features | • Tech Debt - Item 1 |  |  | • Item 2 |  |  | • Item 3 |  |  | • Item 4 [PLACE HOLDER] |  |  | • Item 5 [PLACE HOLDER] • Item 6 |  |  | • Item 7 • Item 8 • Item 9 [PLACE HOLDER] • Item 10 |  |  | • Item 11 • Item 12 [PLACE HOLDER] |  |  | • Item 13 • Bug Fixes • End to End testing
37 SP
milestones mainly for STR or CodeSoure etc. End date in delivery for SK or ver

## Sprints Board
Sprint 1 | Velocity : | 36 | Sprint 2 | Velocity : | 36 | Sprint 3 | Velocity : | 36
| Load : | 36 |  | Load : | 36 |  | Load : | 36
Legends:
Enhancements
Regulatory
Technical Debit
Bug Fixes
Support\Unscheduled Maintainace
Spike
Support\Unscheduled Maintainace = TM1, TM2 | 2 |  | Support\Unscheduled Maintainace = TM1, TM2 | 2 |  | Support\Unscheduled Maintainace = TM1, TM2 | 2
Totals
Sprint 4 | Velocity : | 36 | Sprint 5 | Velocity : | 36 | Sprint 6 | Velocity : | 36
| Load : | 36 |  | Load : | 36 |  | Load : | 36
Support\Unscheduled Maintainace = TM1, TM2 | 2 |  | Support\Unscheduled Maintainace = TM1, TM2 | 2 |  | Support\Unscheduled Maintainace = TM1, TM2 | 2
Sprint 7 | Velocity : | 36 | Sprint 8 (1 WK HIP) | Velocity : | 18
| Load : | 36 |  | Load : | 18
Support\Unscheduled Maintainace = TM1, TM2 | 2 |  | Support\Unscheduled Maintainace = TM1, TM2 | 2

## Risks and Dependencies
Risks
# | ROAM | RISK | POSSIBILITY \ IMPACT | MITIGATION PLAN
1
2
3
4
5
6
7
8
9
10
Dependencies
# | Contact and Team | Dependency Description | Date Estimated | Impact
1
2
3
4
5
Note on C3: Pritesh Patel: ROAM = Resolve, Own, Accept, Mitigate
Note on E3: Pritesh Patel: Low, Medium, High

## Sprints Board Breakdown
Sprint 1 |  |  | DEV |  | QA |  | Velocity : | 36 | Sprint 2 |  |  | DEV |  | QA |  | Velocity : | 36 | Sprint 3 |  |  | DEV |  | QA |  | Velocity : | 36
2017-01-17 | - | 2017-01-30 | BT | BJ | SC | PR | Load : | 36 | 2017-01-31 | - | 2017-02-13 | BT | BJ | SC | PR | Load : | 36 | 2017-02-14 | - | 2017-02-27 | BT | BJ | SC | PR | Load : | 36
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  | Legends:
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  | Enhancements
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  | Regulatory
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  | Technical Debit
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  | Bug Fixes
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  | Support\Unscheduled Maintainace
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  | Spike
Support\Unscheduled Maintainace |  |  | 1 | 1 |  |  | 2 |  | Support\Unscheduled Maintainace |  |  | 1 | 1 |  |  | 2 |  | Support\Unscheduled Maintainace |  |  | 1 | 1 |  |  | 2
|  |  | 1 | 1 | 0 | 0 | 2 |  |  |  |  | 1 | 1 | 0 | 0 | 2 |  |  |  |  | 1 | 1 | 0 | 0 | 2
|  |  | 9 | 9 | 8 | 8 | [5 empty] | 9 | 9 | 8 | 8 | [5 empty] | 9 | 9 | 8 | 8
|  |  | 10 | 10 | 8 | 8 | [5 empty] | 10 | 10 | 8 | 8 | [5 empty] | 10 | 10 | 8 | 8
Sprint 4 |  |  | DEV |  | QA |  | Velocity : | 36 | Sprint 5 |  |  | DEV |  | QA |  | Velocity : | 36 | Sprint 6 |  |  | DEV |  | QA |  | Velocity : | 36
2017-02-28 | - | 2017-03-13 | BT | BJ | SC | PR | Load : | 36 | 2017-03-14 | - | 2017-03-27 | BT | BJ | SC | PR | Load : | 36 | 2017-03-28 | - | 2017-04-10 | BT | BJ | SC | PR | Load : | 36
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
0
0
0
Support\Unscheduled Maintainace |  |  | 2 |  |  |  | 2 |  | Support\Unscheduled Maintainace |  |  | 1 | 1 |  |  | 2 |  | Support\Unscheduled Maintainace |  |  | 1 | 1 |  |  | 2
|  |  | 2 | 0 | 0 | 0 | 2 |  |  |  |  | 1 | 1 | 0 | 0 | 2 |  |  |  |  | 1 | 1 | 0 | 0 | 2
|  |  | 8 | 10 | 8 | 8 | [5 empty] | 9 | 9 | 8 | 8 | [5 empty] | 9 | 9 | 8 | 8
|  |  | 10 | 10 | 8 | 8 | [5 empty] | 10 | 10 | 8 | 8 | [5 empty] | 10 | 10 | 8 | 8
Sprint 7 |  |  | DEV |  | QA |  | Velocity : | 36 | Srpint 8 (1 WK HIP) |  |  | DEV |  | QA |  | Velocity : | 18
2017-04-11 | - | 2017-04-24 | BT | BJ | SC | PR | Load : | 36 | 2017-04-25 | - | 2017-05-01 | BT | BJ | SC | PR | Load : | 18
[7 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0
[7 empty] | 0 | [8 empty] | 0
Support\Unscheduled Maintainace |  |  | 1 | 1 |  |  | 2 |  | Support\Unscheduled Maintainace |  |  | 1 | 1 |  |  | 2
|  |  | 1 | 1 | 0 | 0 | 2 |  |  |  |  | 1 | 1 | 0 | 0 | 2
|  |  | 9 | 9 | 8 | 8 | [5 empty] | 4 | 4 | 4 | 4
|  |  | 10 | 10 | 8 | 8 | [5 empty] | 5 | 5 | 4 | 4

## Release Breakdown - Mgmt
Enhancements | [5 empty] | Total (SP) | 270
Secondary Claim edit (COB) for balance validation
Patient Estimates (fee estimation) for transparencey compliance
Regulatory (CAP)
State Report - Non Common - Common - MO, SC, FL
2017 ASCA Benchmarking Report Updates
ASC 13 Normothermia Outcome Measure - Placeholder
ASC 14 Unplanned Anterior Vitrectomy - Placeholder
ASC 15a-e OAS CAHPS - Placeholder
Automate Submission/Transmission for OAS CAHPS Data - PLACEHOLDER
NV - SSN update
CT - White paper change for payer codes
Regulatory (Non-CAP)
Technical Debit
SQL 2016
Windows 2016
Setting up environments
Moving test cases from JIRA to TFS
Maintenance
136 - NV Country Code update
172 - X12P Must pull Loop 2300 HI*BP when ANES service are being billed
140 - Update X12i map to indicate if 2330B REF*2U is populated then it will pull
777 - SIS (X12P/X12I) 2330B NM109 must be specific payer ID when the sec payer mandates.
Stretch goal - EFT not appearing in all locations in Billing Module
Support\Unscheduled Maintenance
|  | Category | Story Points | Allocation % | Total Allocation %
| CAP | Enhancements | 36 | 13.33% | 80%
|  | Regulatory (CAP) | 124 | 45.93%
|  | Technical Debit | 56 | 20.74%
| Non-CAP | Regulatory (Non-CAP) | 0 | 0% | 11.48%
|  | Maintenance | 17 | 6.296%
|  | Support\Unscheduled Maintainace | 14 | 5.185%
|  | Total SP | 247 | 91.48% | 91.48%
Total SP : 247
Total SP : 247

## Commit vs Achieved Chart - Mgmt
Sprint Name | Sprint Start | Sprint End | SP Committed | SP Achieved | % Delivered
Sprint 1 | 2017-01-17 | 2017-01-30 | 36 | 0 | 0%
Sprint 2 | 2017-01-31 | 2017-02-13 | 36 | 0 | 0%
Sprint 3 | 2017-02-14 | 2017-02-27 | 36 | 0 | 0%
Sprint 4 | 2017-02-28 | 2017-03-13 | 36 | 0 | 0%
Sprint 5 | 2017-03-14 | 2017-03-27 | 36 | 0 | 0%
Sprint 6 | 2017-03-28 | 2017-04-10 | 36 | 0 | 0%
Sprint 7 | 2017-04-11 | 2017-04-24 | 36 | 0 | 0%
Total |  |  | 252 | 0 | 0%

## Lookups
Sprint Start Date: | 2017-01-17
Sprint Length | 14
Sprint Name | Sprint Start | Sprint End
Sprint 1 | 2017-01-17 | 2017-01-30
Sprint 2 | 2017-01-31 | 2017-02-13
Sprint 3 | 2017-02-14 | 2017-02-27
Sprint 4 | 2017-02-28 | 2017-03-13
Sprint 5 | 2017-03-14 | 2017-03-27
Sprint 6 | 2017-03-28 | 2017-04-10
Sprint 7 | 2017-04-11 | 2017-04-24
Srpint 8 (1 WK HIP) | 2017-04-25 | 2017-05-01
Formulas:
Sprint Start = [Sprint End, row above]+1
Sprint End = [Sprint Start]+D3-1

## Work Distribution
|  | Sprint 1 |  | Sprint 2 |  | Sprint 3 |  | Sprint 4 |  | Sprint 5 |  | Sprint 6 |  | Sprint 7 |  | Sprint 8 |  | Sprint 9
| Capacity | Track | Capacity | Track | Capacity | Track | Capacity | Track | Capacity | Track | Capacity | Track | Capacity | Track | Capacity | Track | Capacity | Track
Pavithra | 8 | 8 | 8 | 8 | 7 | 7 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 4
Sherri | 8 | 8 | 7 | 7 | 8 | 8 | 4 | 4 | 8 | 8 | 6 | 6 | 8 | 8 | 6 | 1 | 4 | 1
Bidya | 8 | 8 | 7 | 7 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 4 | 1
Bala | 8 | 8 | 7 | 7 | 6 | 6 | 5 | 5 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 1 | 4 | 1